## Event Planning
Event Planning
Event Name | 2025 HYSTA Founders Club Open Day: AI Agents Unleashed – Turning Hype into Impact
Date & Time | 2025-05-10
Format (In-person/Hybrid/Virtual) | In-person
Speakers/Guests | 1 keynote, 4 panelist
Agenda | Event Agenda
Target Audience | founder / VC
Expected Attendance | 100
Objectives/KPIs
Lead person | Jack, Danning, Qi, Jennifer
Supporting team | Founders Club
Luma | Account and password
Canva | Jennifer
LinkedIn | Vivian
Newsletter | Vivian
WeChat | Vivian

## On-Site Preparation
Pre-Event - On-Site Preparation |  | Role assignments
Materials: Name tags |  | Danning
Materials: Check-in list |  | Danning
Materials: Catering arrangements | 20 HeyTea 1 box of water | Felix?
Media & Tech: Event slide deck |  | Jennifer, Meng Su
Media & Tech: Microphones / Projector setup |  | Jennifer, Meng Su
Media & Tech: Internet & power backup |  | Jennifer, Meng Su

## Event Logistics
Pre-Event - Event Logistics | Role assignments
Speaker Coordination: Confirm schedule, agenda, location | Danning, Jiaqi
Speaker Coordination: Headshot + bios prepared | Danning, Jiaqi
Speaker Coordination: Slides or deck ready | Danning, Jiaqi
Calendar Invites: Internal team | Danning, Jiaqi
Calendar Invites: Guest speakers | Danning, Jiaqi
Registration Management: Confirm sign-ups | Qi
Registration Management: Send 1st confirmation emails | Qi
Registration Management: Send reminders (parking, check-in info) | Qi
Q&A Preparation: Curated list of questions | Crystal

## Marketing & Promotion
Pre-Event - Marketing & Promotion | Role assignments
Poster Design & Prep: Guest/moderator portrait | Danning, Jiaqi
Poster Design & Prep: QR code for registration | Qi
Newsletter & Social Media Content: Poster | Jennifer
Newsletter & Social Media Content: Company/startup highlights | Danning, Jiaqi
Newsletter & Social Media Content: Registration link | Qi
Newsletter & Social Media Content: Event start & end time | Qi
Social Media Distribution: Luma/Eventbrite | Qi
Social Media Distribution: Newsletter | Vivian
Social Media Distribution: Sponsor email blasts | -
Social Media Distribution: WeChat, LinkedIn, The Redbook? | Vivian
Third-party Partners/KOLs | -
Publishing Timeline: T-14 / T-7 / T-1 posts | Vivian
Content Creation Responsibilities: Design / Copywriting / Approval | Danning, Jiaqi

## Event Execution
Event Execution | Role assignments
Venue Setup: tables, signage, branding, seating | Danning, Jiaqi, Qi, Jennifer, Meng
Check-in Station Setup: Attendee & speaker check-in | Danning, Jiaqi
Food & Beverage Setup | Jennifer, Qi
Tech Setup: Projector, microphones, camera | Meng, Jennifer
Photo/Video Coverage | Nikita
Run-of-Show Timeline: schedule and owner per item | Jennifer

## Post-Event
Post-Event | Role assignments
Internal recap and debrief | Danning, Jiaqi
Upload video to YouTube | Nikita
Speaker/guest thank-you notes | Danning, Jiaqi
Attendee thank-you email | Danning, Jiaqi
Feedback survey | Qi
Attendee vs. registration analysis | Qi
Social media stats | Vivian
Feedback survey results | Qi
Archive: Photos/videos | Nikita
Archive: Slide decks | Jennifer
Archive: Event run sheet | Qi
Archive: Updated SOP | Qi